## PM 1
Puerto Rico Public Housing Administration
Construction Management Bureau
MONTHLY CONSTRUCTION REPORT # | [7 empty] | Forma AVP-500302
Case OGPe: | [7 empty] | Rev. June 2017
Period Ended
Project Name
Project Address
Project No. |  |  |  |  | Contract No.
Prime Contractor
Resident Engineer
Contracted Inspection
Contracted Architect
Contract Starting Date | [5 empty] | Completion Date
Modified completion dates as per Change Orders
Estimated completion dates
TIME FOR COMPLETION
A. Original | ……………………………………… | [5 empty] | calendar days
B. Additional as per Change Orders |  |  |  | ……………………………………… |  |  | calendar days
C. New time for completion |  |  | ……………………………………… |  |  |  | calendar days
Time consumed to date |  |  | ……………………………………… |  |  |  | calendar days
Percent of time consumed |  |  | ………………………………………
CONTRACT COST
A. Original cost |  | ………………………………………
B. Change Orders # |  |  | to |  | ………….
C. Adjusted cost |  | ………………………………………
VALUE OF CONTRACT WORK PERFORMED
A. Previously |  | …………………………………… |  |  |  |  | %
B. This period |  | …………………………………… |  |  |  |  | %
C. To date | ……………………………………
Percent completed to date |  |  | ……………………………………
DELAYS DUE TO RAIN WEATHER
Previously |  |  | This period |  |  |  | To date
Delays due to other causes this period (be specific)
MONTHLY CONSTRUCTION REPORT # | [8 empty] | Page 2
Reasons why the works are not progressing normally
Detail the more important works performed during this period
Pending problems
Enclosures included in this report
RESPECTFULLY SUBMITTED BY: | [5 empty] | SEAL
Name
Resident Engineer
Signature