## AVP-500501
REGISTRO DE REMISIONES "SUBMITTALS"
Forma AVP-500501 Rev. Junio 2017
| Nombre Proyecto: |  | Res. |  | Gerente del Programa:
| Núm. Proyecto: |  | RQ 00 |  | Contratista General:
| Dirección: |  | , PR |  | A/E:
2017-03-13
| "Submittal" núm. | Descripción del "submittal" |  | Fecha a Someterse según CPM |  | Fecha Sometida | Días de Entrega Tardía
| 1 | C.P.M. Progress Report |  |  |  |  | 0
| 2 | Breakdown for payment |  |  |  |  | 0
| 3 | Lead Based Paint Removal |  |  |  |  | 0
| 4 | Asbestos Removal Works |  |  |  |  | 0
| 5 | Listado de remisiones |  |  |  |  | 0
| 6 | Listado de remisiones revisado |  |  |  |  | 0
| 7 | Safety Plan+Anejo para huracán |  |  |  |  | 0
| 8 | Traffic Control Plan |  |  |  |  | 0
| 9 | Plumbing Fixtures |  |  |  |  | 0
| 10 | Plumbing Fixtures Temporary |  |  |  |  | 0
| 11 | Pad Mounted Transformers |  |  |  |  | 0
| 12 | Load Center for Housing Units |  |  |  |  | 0
| 13 | Conduits & Fittings for electrical works |  |  |  |  | 0
| 14 | Junctions boxes, cabinets,etc. electrical |  |  |  |  | 0
| 15 | Concrete Poles |  |  |  |  | 0
| 16 | Smoke Detector |  |  |  |  | 0
| 17 | GFI Receptacle |  |  |  |  | 0
| 18 | Outlet Boxes & Covers |  |  |  |  | 0
| 19 | Conduit and fitting |  |  |  |  | 0
| 20 | Cabinets, Junction Boxes & Pull boxes |  |  |  |  | 0
| 21 | Concrete Poles |  |  |  |  | 0
| 22 | Fluorescent Lighting Fixtures |  |  |  |  | 0
| 23 | Fluorescent Electronic Ballast |  |  |  |  | 0
| 24 | Fluorescent Lamps |  |  |  |  | 0
| 25 | Incandescent Lighting Fixtures |  |  |  |  | 0
| 26 | Incandescent Lamps |  |  |  |  | 0
| 27 | Exist Sings |  |  |  |  | 0
| 28 | Luminaires |  |  |  |  | 0
| 29 | Lamps |  |  |  |  | 0
| 30 | Ballast |  |  |  |  | 0
| 31 | Load Center for Housing Units, Meter |  |  |  |  | 0
| 32 | Banks & TTC Box |  |  |  |  | 0
| 33 | Plumbing Fixtures (Temporary) |  |  |  |  | 0
| 34 | Pad Mounted Transformer |  |  |  |  | 0
| 35 | Plumbing Fixtures |  |  |  |  | 0
| 36 | Hardware Modules |  |  |  |  | 0
| 37 | Lead Based Paint Removal |  |  |  |  | 0
| 38 | Asbestos Removal Works |  |  |  |  | 0
| 39 | Traffic Control Plan (revised) |  |  |  |  | 0
| 40 | Hardware Permanent Units |  |  |  |  | 0
| 41 | Breakdown for Payment (revised) |  |  |  |  | 0
| 42 | Concrete Mix Design |  |  |  |  | 0
| 43 | Reinf. Steel Mill Certificate |  |  |  |  | 0
| 44 | Lumber mill (aprobado con notas) |  |  |  |  | 0
| 45 | Plywood (aprobado con notas) |  |  |  |  | 0
| 46 | Metal Anchorage |  |  |  |  | 0
| 47 | Samples of Materials & Roll felt Roofing |  |  |  |  | 0
| 48 | Storm drainage conc. Pipe & fittings |  |  |  |  | 0
| 49 | PVC Storm drainage System & fittings |  |  |  |  | 0
| 50 | Pre-cast manholes & catch basins |  |  |  |  | 0
| 51 | Kitchen Cabinets - Temporary |  |  |  |  | 0
| 52 | Smoke Detectors |  |  |  |  | 0
| 53 | Ventanas aluminio |  |  |  |  | 0
| 54 | Water Heaters |  |  |  |  | 0
| 55 | Water Hammer a rrestors, access covers |  |  |  |  | 0
| 56 | Plumbing Fixtures - Temporary |  |  |  |  | 0
| 57 | Plumbing Fixtures |  |  |  |  | 0
| 58 | Wires & Cables aprobado con notas |  |  |  |  | 0
| 59 | Hardware Modules |  |  |  |  | 0
| 60 | Hardware Permanent Modules |  |  |  |  | 0
| 61 | Puertas y marcos de madera |  |  |  |  | 0
| 62 | Plumbing Fixtures |  |  |  |  | 0
| 63 | Plumbing Fixtures Community Bldg. |  |  |  |  | 0
| 64 | Plumbing Fixtures Permanet |  |  |  |  | 0
| 65 | PVC Copper pipes and jointing material |  |  |  |  | 0
| 66 | Electric Meter Banks (temporary modules) |  |  |  |  | 0
| 67 | Plumbing Fixtures (permanent) |  |  |  |  | 0
| 68 | Geotextile products |  |  |  |  | 0
| 69 | Portland Cement Terrazo |  |  |  |  | 0
| 70 | Quarry Tile & Ceramic |  |  |  |  | 0
| 71 | Accesorios Baños Permanentes |  |  |  |  | 0
| 72 | Herrajes Permanentes |  |  |  |  | 0
| 73 | Exit Signs |  |  |  |  | 0
| 74 | Porcelain Reflectors (lamps) |  |  |  |  | 0
| 75 | Stair Nosing (Permanent) |  |  |  |  | 0
| 76 | Vinyl Coated Cable |  |  |  |  | 0
| 77 | Roof Scuttle |  |  |  |  | 0
| 78 | 6", 8" Conc. Blocks |  |  |  |  | 0
| 79 | Accesorios Baños (Permanentes) |  |  |  |  | 0
| 80 | Herrajes para puertas (Permanentes) |  |  |  |  | 0
| 81 | Doors & Frames |  |  |  |  | 0
| 82 | Accesorios Baños Permanentes |  |  |  |  | 0
| 83 | Herrajes para puertas (Permanentes) |  |  |  |  | 0
| 84 | Doors & Frames |  |  |  |  | 0
| 85 | Service Sink |  |  |  |  | 0
| 86 | Emergency Lighting Fixtures (Temporary) |  |  |  |  | 0
| 87 | Pintura (Permanente) |  |  |  |  | 0
| 88 | Hardware (permanente) |  |  |  |  | 0
| 89 | Modified Bituminous Membrane |  |  |  |  | 0
| 90 | Flashing & Sheet Metal |  |  |  |  | 0
| 91 | Reinforced Steel Shop Drawings |  |  |  |  | 0
| 92 | Outlet, Boxes & Covers |  |  |  |  | 0
| 93 | Soportes de lavamanos permanentes |  |  |  |  | 0
| 94 | Modified Bituminous Membrane |  |  |  |  | 0
| 95 | Flashing & Sheet Metal |  |  |  |  | 0
| 96 | Aluminum Windows (Permanent) |  |  |  |  | 0
| 97 | Pintura |  |  |  |  | 0
| 98 | Toilet and Bath Accessories |  |  |  |  | 0
| 99 | Floor Drain |  |  |  |  | 0
| 100 | Water hammer arrestors, access doors |  |  |  |  | 0
| 101 | Mod. Bituminous Membrane Roof Insul. |  |  |  |  | 0
| 102 | Impearmeabilización para pisos |  |  |  |  | 0
| 103 | Bonding agent para empañetados |  |  |  |  | 0
| 104 | Pintura |  |  |  |  | 0
| 105 | Acrylic latex bonding agent-sellado piso |  |  |  |  | 0
| 106 | Toilet and Bath Accessories (color) |  |  |  |  | 0
| 107 | Modified Bituminous Membrane Roofing |  |  |  |  | 0
| 108 | Ceramica de piso/pared - Edif. Adm. |  |  |  |  | 0
| 109 | MSDS Data for primer |  |  |  |  | 0
| 110 | Bituminous Prime Coat |  |  |  |  | 0
| 111 | Bituminous Concrete |  |  |  |  | 0
| 112 | Recept. e Interruptores elect. |  |  |  |  | 0
| 113 | Counter Fire Doors |  |  |  |  | 0
| 114 | Counter Fire Doors |  |  |  |  | 0
| 115 | Accordion Folding Partitions |  |  |  |  | 0
| 116 | Mail Boxes |  |  |  |  | 0
| 117 | Toilet Partitions |  |  |  |  | 0
| 118 | Load Center (Comm. Bldg.) |  |  |  |  | 0
| 119 | Plumbing Fixture (Escutcheo Plates) |  |  |  |  | 0
| 120 | Fire Extinguisher Cabinet |  |  |  |  | 0
| 121 | Acoustical Ceiling & Suspection System |  |  |  |  | 0
| 122 | Cabinet & Countertops & Hardware |  |  |  |  | 0
| 123 | Ventanas aluminio - Permanente |  |  |  |  | 0
| 124 | Water Heater - Administración |  |  |  |  | 0
| 125 | Accordion Folding Partitions |  |  |  |  | 0
| 126 | Kitchennette |  |  |  |  | 0
| 127 | Mail Boxes |  |  |  |  | 0
| 128 | Folding door (community building) |  |  |  |  | 0
| 129 | Chain Link Fencing Components |  |  |  |  | 0
| 130 | Acoustical Ceiling & Suspension System |  |  |  |  | 0
| 131 | Ornamental blocks |  |  |  |  | 0
| 132 | Fregaderos Impedidos |  |  |  |  | 0
| 133 | Folding doors - Comm. Bldg. |  |  |  |  | 0
| 134 | Flashing Ventilaciones techo |  |  |  |  | 0
| 135 | Air Conditioned Machines |  |  |  |  | 0
| 136 | Mop and broom holders |  |  |  |  | 0
| 137 | Clip de fregaderos |  |  |  |  | 0
| 138 | Paint (Comm.Bldg.) |  |  |  |  | 0
| 139 | Hardware lock for escape doors (H.C.) |  |  |  |  | 0
| 140 | Portland cement terrazzo for H.C.blind apt. |  |  |  |  | 0
| 141 | Community Bldg. Saddle |  |  |  |  | 0
| 142 | Community Bldg. Saddle |  |  |  |  | 0
| 143 | Granitifiandre giallo A.D.A. color -P120 |  |  |  |  | 0
| 144 | American Flagpole 94138-014 |  |  |  |  | 0
| 145 | Playground facilities |  |  |  |  | 0
| 146 | Robe Hook Gamco 754 |  |  |  |  | 0
| 147 | White Silty Sand |  |  |  |  | 0
| 148 | Pale Yellow Silt Sand / Bond Terrazo |  |  |  |  | 0
| 149 | Pale Yellow Silt Sand / Empañete |  |  |  |  | 0
| 150 | Basketball Court Steel Building |  |  |  |  | 0
| 151 | Service Sinck Faucet Eljer |  |  |  |  | 0
| 152 | Color Samples Metal Deck |  |  |  |  | 0
| 153 | Basketball Court Steel Building |  |  |  |  | 0
| 154 | Footing Detail - Basketball Court |  |  |  |  | 0
| 155 | Caulking for bldg. Expansion Joints |  |  |  |  | 0
| 156 | Muestra rotulo para ciego |  |  |  |  | 0
| 157 | Adoquin para ciego |  |  |  |  | 0
| 158 | Quikrete-Grout |  |  |  |  | 0
| 159 | Hand Held Shower #151 - bldg. MM |  |  |  |  | 0
| 160 | Rotulo Sistema Braille-Naim |  |  |  |  | 0
| 161 | Hand Held Shower #151 - Carta Adolfo S. Pagan |  |  |  |  | 0
| 162 | Hand Held Shower #151-(ADA) |  |  |  |  | 0
| 163 | Canasto Baloncesto, Pintura, Zapata, Tablero Cancha |  |  |  |  | 0
| 164 | Detalle zapata, tubo baloncesto y Volleyball |  |  |  |  | 0
165
166
167
168
169
170